## Sprint Backlog
Task | Associated User Story | Assigned To… | Estimate | Actual
Add filter search bar to UI | Add Filter | Destiny | 0.25 | 0.1
Add "Add Filter" button to UI | Add Filter | Destiny | 0.25 | 0.1
Add "Clear Filters" button to UI | Clear Filters | Destiny | 0.25 | 0.1
Add radio buttons for Seller, Category, and Distance filters | Filter Discounts | Mariah | 0.25 | 0.1
Add star icon next to Seller names in UI output | Favorite a Seller | Brianna | 0.25 | 0.1
Implement Add Filter button functionality | Add Filter | Brianna | 2 | 1
Implement Delete Filter button functionality | Delete Filter | Mariah | 2 | 2
Implement Clear Filters button functionality | Clear Filters | Destiny | 1.5 | 1
Implement Favorite Seller functionality | Favorite Seller | Brianna |  | 1
Implement Radion Button Functionality for filter | Filter Discounts | Destiny |  | 1.5
Total Time To Complete |  |  | 6.75 | 7