## Sprint Backlog
Task | Associated User Story | Assigned To… | Estimate
Add filter search bar to UI | Add Filter | Destiny | 0.25
Add "Add Filter" button to UI | Add Filter | Destiny | 0.25
Add "Clear Filters" button to UI | Clear Filters | Destiny | 0.25
Add radio buttons for Seller, Category, and Distance filters | Filter Discounts | Mariah | 0.25
Add star icon next to Seller names in UI output | Favorite a Seller | Brianna | 0.25
Implement Add Filter button functionality | Add Filter | Brianna | 2
Implement Delete Filter button functionality | Delete Filter | Mariah | 2
Implement Clear Filters button functionality | Clear Filters | Destiny | 1.5
Total Time To Complete |  |  | 6.75